## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 14.04.2021 - 27.04.2021
Group Number |  | 31
Participant 1 |  | Dohnalek, Raphael
Participant 2 |  | Duskanich, Michael
Participant 3 |  | Meindl, Tobias
Participant 4 |  | Goeroeg, Jessica
Participant 5 |  | Kern, Konstantin |  |  |  |  | Vorgenommene Storypoints | Erreichte Storypoints | Differenz
Mentor |  | Richter, Georg |  |  |  |  | 20 | 12 | -8
Req ID | short description [opt] | Estimate [sp] | Real Efort [h] | Passed | Failed | remarks
1 | Game Upload - File upload | 5 | 0:31 | 1 | 0
2 | Game Upload - Frontend, Database, Backend | 3 | 1:34 | 1 | 0
3 | Forum and Front Page - Refactoring | 2 | 1:52 | 1 | 0
4 | Profilepicture upload - Fronted | 5 | 2:52 | 1 | 0
5 | Nav Bar | 2 | 1:17 | 1 | 0
|  | 12 | 5:14 | 0 | 0